N2I September Launch — Social Media Campaign Strategy

1. Key Dates

Update (Aug 12): campaign start slipped to today. Exact registration deadline is still unconfirmed — Mr Samuel indicated "first week of September." This plan uses 5 September as a placeholder deadline and 12 September as a placeholder announcement date.

| Date | Milestone |
| --- | --- |
| Aug 12 (today) | Introduce n2i post across LinkedIn, Instagram, YouTube |
| Aug 11 - 17 | Launch — program tracks, eligibility, "introduce N2I / our story," first team intro |
| Aug 18 - 24 | Proof “why AI for JHS," STEM/STEAM/STREAM, gender-gap stats, mentor content, testimonials. |
| Aug 25 - 31 | Push — daily countdown, reminder posts, share application link |
| Sep 1 - 5 | Final call — daily posts, Story countdown, deadline closes |
| Sep 6 - 11 | Review period — optional behind-the-scenes "reviewing applications" post |
| Sep 12 | Announcement day — cohort reveal + welcome content |

Note: dates below are provisional

2. Campaign Track A — Call for Students

- Goal

Drive 100 qualified registrations from JHS students and SHS graduates, before the (to-be-confirmed) early-September deadline.

- Key messages

N2I bridges the gap between classroom learning and real, employable tech skills.

Free, fully online — Web Development and AI/Machine Learning tracks. Requires access to a PC and internet.

Proven track record — pilot programs since 2025, and one of Ghana's first Google Gemini AI Certified (K12) students.

Clear, simple call to action: apply before the deadline (date to be confirmed).

Day-by-day schedule

Proposed Calendar

| Date | Content |
| --- | --- |
| Aug 12 | "Applications open" post — all 3 platforms |
| Aug 12-13 | "Introduce N2I — our story" post |
| Aug 14 | First team member intro |
| Aug 15-16 | Theory of change / N2I 2025 Annual Report highlights |
| Aug 17 | Graphic testimonial — past learner or parent |
| Aug 18 | "Why should JHS students learn AI?" explainer |
| Aug 19 | STEM vs STEAM vs STREAM content |
| Aug 20 | Second team member intro / trainer profile |
| Aug 21 | Female STEM gap statistics + direct call for girls to apply |
| Aug 22 | "Why a mentor makes a difference" |
| Aug 23-24 | Video or graphic recommendation — team members or past learner |
| Aug 25-31 | Daily Story countdown begins. Reminder posts Aug 25, 28, 31 + reshare application link. One more team intro. One more testimonial (parent or learner). |
| Sep 1-4 | Daily posts + Story countdown sticker |
| Sep 5 | "Closes tonight” last chance post (placeholder deadline, confirm exact date with Mr Samuel) |
| Sep 6-11 | Review period — optional "reviewing applications" post; catch-up space for any skipped content |
| Sep 12 | Cohort announcement — reveal across all platforms |

After Sep 12 monthly team + participant spotlights, video testimonials from the new cohort.

3. Campaign Track B — Call for Sponsors & Partners

Goal

Run in parallel with the student registration push primarily on LinkedIn, to attract funding and partnership interest as N2I scales toward its permanent Community STEM Innovation Centre.

Key messages

N2I has a proven, low-cost delivery model with measurable outcomes — pilot programs since 2025 and a national first in Gemini AI K12 certification (exact learner numbers to be confirmed with the team).

We are scaling into a permanent Community STEM Innovation Centre and a structured digital-and-AI skills pipeline, including reaching rural areas with connectivity constraints.

Clear ask: partner meetings, in-kind support, or funding to help launch and sustain the new cohort.

Content plan

| Phase | Content | Format / Cadence |
| --- | --- | --- |
| Week 1-2 | Impact-focused LinkedIn post — the case for support, framed around the new cohort launching in September | 1-2 LinkedIn posts, reshared by team members' personal profiles |
| Week 3 | "Behind the scenes" post showing the scale of demand for the program | 1 LinkedIn post |
| Ongoing | Direct outreach to identified funders/partners (IDP, Spark, and others), supported by a one-pager / media kit | Not public |

4. Measurement

Registrations: number of completed applications tracked against the (to-be-confirmed) September deadline, against the 100-spot target.

Engagement: likes, comments, shares, and Story replies on call-for-students content.

Reach: profile visits and link clicks

Partnerships: number of inquiries or meetings booked from the sponsor/partner track.

5. Graphic Assets Needed (mapped to campaign weeks)

Launch graphic “Applications open”

Success story / testimonial graphic (Week 2)

Countdown graphics — 10 days, 5 days, final day (Week 3-4)

Cohort announcement graphic – nil

Call-for-partners impact graphic

"Who we are" story graphic, team template, and partner template